## Checklist
Reseller Program Checklist
| Category |  |  |  | Time Frame | Schedule | Assigned To | Notes
Status | Program Definition & Setup
|  | Define program (levels, agreement, policies) |  |  | 1 hour
Setup Portal
|  |  | Install Wordpress (fresh install) |  | 30 min
|  |  | Clone portal |  | 45 min
|  |  | Personalize - logo, etc. |  | 1 hour
|  |  | Setup emails and phone (partners@company.com), separate phone line |  | 30 min
|  |  | Test portal (ALL forms) |  | 30 min
|  | Setup policies (review & edit every page of portal) |  |  | 2 hours
|  | Create SaaSMAX Profile (if applicable) and Ideal Partner Configuration |  |  | 2 hours
|  | Create outstanding deliverables for portal |  |  | Varies
|  |  | Competitive Matrix |  | 3 weeks |  |  | If don't have one
|  |  | PowerPoint |  | 1 day - 1 week |  |  | Time dependant on persuasive doc
|  |  | 25/50/100 word description |  | 2 hours
|  |  | Market Info |  | 2 hours
|  |  | Logo, graphics |  | 30 min
|  |  | Price list (PDF) |  | 1 hour
|  |  | Create product demo script |  | 4 hours
|  |  | Other (white papers, case studies, videos) |  | Varies
|  | Review EVERY page of portal site - confirm it is complete |  |  | 1 hour
|  | Determine reseller margin & how will get paid |  |  | 2 hours
|  | Confirm the system and process for partner payments |  |  | 1 hour
|  | Create reseller approval email |  |  | 1 hour
|  | Create recruiting emails (for previous interest, new, competititors) |  |  | 2 hours
|  | Create orientiaton demo script |  |  | 5 min
|  | Determine NFR process (how to get partner license #'s) |  |  | 1 hour
|  | Put a link to reseller portal / application from main site - ready to recruit |  |  | 10 min
Recruiting
|  | Complete SaaSMAX IPC (Ideal Partner Configuration) |  |  | 15 min |  |  | info.saasmax.com/ideal-partner-configuration-form
Database
|  |  | Compile list of any previously interested partners |  | 1 hour
|  |  | Compile Chanimal database |  | 1 hour
|  |  | Compile competitors resellers (internal & Navin) |  | 1 week |  |  | A counter-strike - weakens their program, strengthens yours
|  |  |  | Finalize reseller database fields (Chanimal sample) | 3 hours
Systems
|  |  | Determine CRM systems or spreadsheet |  | 1 hour
|  |  | Mass email system - select & setup |  | 2 hours
|  |  | Import database(s) into email system |  | 1 hour
|  |  | Setup recruiting email template(s) |  | 30 min
|  |  | Call our phone numbers, send ourselves emails - confirm they are all active |  | 15 min
|  |  | Confirm channel people are getting the emails from the partner FORMS |  | 15 min
Email campaign
|  |  | Determine when it will go out (days and times (typically work hours)) |  | 30 min
|  |  | Start first email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 2 hours
|  |  | Start 2nd email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 1 hour
|  |  | Start 3rd email |  | 30 min
|  |  | Clean out bounce backs, remove names, applied/responded |  | 1 hour
Portal Training
|  |  | Wordpress overview & training (if don't know how to edit) - YouTube |  | 3 hours
|  |  | Know how to add reseller |  | 30 min
|  |  | Know how to manage forum |  | 1 hour
|  |  | Can add a page, set permissions |  | 30 min
|  |  | Can add a contact to reseller locator |  | 15 min
|  | Finalize Reseller Follow-up Worksheet |  |  | 30 min
Set up new resellers
|  |  | Get NFR information |  | 15 min
|  |  | Add reseller to portal (will send out email) |  | 15 min
|  |  | Determine webinar date |  | 15 min
|  |  | Edit approval email (NFR, password, webinar date) and send |  | 15 min
Orientation
|  | Learn the product |  |  | 6 hours
|  | Learn the product demo script |  |  | 3 hours
|  | Learn the product orientation demo - repurpose script |  |  | 3 hours
|  | Test run - orientation (with portal and product demo (record each)) |  |  | 1 hour
|  | Know how the reseller will place the order |  |  | 30 min
|  | Determine system for reseller orientation (Skype, GoToMeeting/GoToWebinar, etc.) |  |  | 30 min
|  | Conduct orientation with each partner (1 on 1, webinars) - follow reseller worksheet |  |  | 1 hour each
Enablement
|  | Create reseller SEO - landing page template |  |  | 3 hours
|  | Create reseller email template |  |  | 3 hours
|  | Repurpose the lead referral template |  |  | 2 hours
|  | Setup marketing meeting with reseller |  |  | 15 min each
|  | Conduct marketing meeting (setup 3 promos (setup promo calendar)) |  |  | 1 hour each
Conduct marketing meeting - SEO landing page template, email campaign
2nd Setup
Confirm reseller has product listed on website
Add reseller to reseller locator (within portal)
Send email to reseller confirming now listed in locator
Create thank you email - for reseller's first sale, send to reseller
Create thank you email for 2nd sale - send to reseller
Create newsletter template, send monthly newsletter (informatl)
Setup levels, certification, quotas
Define reseller levels (usually at 6 month mark)
Review existing reseller sales, determine break points
Define certification program
Review reseller FAQs, additional training areas
Determine how to train/certifiy resellers
Determine systems to use (LMS)
Create training material (PowerPoint, manuals)
Create reseller levels and certification policies
Create reseller email to announce program
Setup meeting with ALL partners (1 on 1, group webinars) to review new levels and certification
Conduct partner meetings (with EVERY partner) - use worksheet to confirm attendance

## Instructions
Copyright © 2019, Chanimal™, all rights reserved. Also licensed to SaaSMAX.
The checklist helps ensure you complete ALL of the definition, recruiting, orientation and enablement
steps to create a world-class reseller partner program.
More detail can be found in your master plan of action.